## Sheet1
Description | Start Date | End Date | Duration (Days) | Extended Description | Responsibility
Task 1 | 18/4/2015 | 22/4/2015 | 5 | Complete UI design for the home page. | Front End team
Task 2 | 18/4/2015 | 19/4/2015 | 2 | Allow user to sign up in Rails application. | Rohan
Task 3 | 20/4/2015 | 20/4/2015 | 1 | Test the user sign up. | Front End team
Task 4 | 21/4/2015 | 23/4/2015 | 3 | Allow user to sign in the Rails application (Sessions). | Rohan
Task 5 | 22/4/2015 | 25/4/2015 | 4 | Complete UI design for the profile page | Front End team
Task 6 | 24/4/2015 | 27/4/2015 | 4 | Allow music to display algorithmically and dynamically on the front page. | Rohan
Task 7 | 24/4/2015 | 27/4/2015 | 4 | Allow users to maintain their profile, follow other users and view other profiles and show music on profile. | Vui Chee
Task 8 | 24/4/2015 | 27/4/2015 | 4 | Create forms which will be used by the User to upload images/music with information. | Alex
Task 9 | 24/4/2015 | 27/4/2015 | 4 | Work on implementing an instance of jplayer (audio player) which will play music on the homepage. | Josh
Task 10 | 25/4/2015 | 27/4/2015 | 3 | Complete UI design when you click music/album + comments | Front End team
Task 11 | 27/4/2015 | 27/4/2015 | 1 | Test all the functionalities implemented form Task 3 to Task 7. | Front End team
Task 12 | 28/4/2015 | 30/4/2015 | 3 | Provide the functionality for users to rate music/download music +Donate to artists | Rohan
Task 13 | 28/4/2015 | 30/4/2015 | 3 | Provide the functionality for users to comment on profiles/music and respond to personal messages. | Vui Chee
Task 14 | 28/4/2015 | 30/4/2015 | 3 | Implement search functionality for users to search artists/music/profiles | Alex
Task 15 | 2015-01-05 | 2015-05-05 | 5 | Allow users to maintain(CRUD) multiple playlist using cookies + sessions. | Back End + Front End teams
Task 16 | 2015-05-05 | 2015-10-05 | 5 | Create a notification system to notify followers of new music + notify when you get a personal message. | Back End team
Task 17 | 2015-10-05 | 2015-12-05 | 2 | Usability testing, White box testing, Unit testing, Functional Testing | Back End + Front End teams
Task 18 | 2015-12-05 | 18/5/2015 | 7 | Reserved for testing + Any changes that may need to be made as a result for testing | Back End + Front End teams
Task 19 | 18/5/2015 | 18/5/2015 | 1 | Submit project!!! | Team

## Sheet2
Description | Start Date | Duration (Days)
Task 1 | 2015-04-18 | 5
Task 2 | 2015-04-18 | 2
Task 3 | 2015-04-20 | 1
Task 4 | 2015-04-21 | 3
Task 5 | 2015-04-22 | 4
Task 6 | 2015-04-24 | 4
Task 7 | 2015-04-24 | 4
Task 8 | 2015-04-24 | 4
Task 9 | 2015-04-24 | 4
Task 10 | 2015-04-25 | 3
Task 11 | 2015-04-27 | 1
Task 12 | 2015-04-28 | 3
Task 13 | 2015-04-28 | 3
Task 14 | 2015-04-28 | 3
Task 15 | 2015-05-01 | 5
Task 16 | 2015-05-05 | 5
Task 17 | 2015-05-10 | 2
Task 18 | 2015-05-12 | 7
Task 19 | 2015-05-18 | 1